{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":16,"n_cols":9,"rows_kept":16,"cut":false,"hidden":false,"merged":[[0,0,0,8],[2,2,2,3],[3,2,3,3],[4,2,4,3],[5,2,5,3],[9,2,9,3],[10,2,10,3],[11,2,11,3],[12,2,12,3],[13,2,13,3],[14,2,14,3],[15,2,15,3],[6,2,8,2]]}
["网站建设工作计划项目时间进度表方案\n\n为了更好落实公司网站建设进度，做如下网站建设计划表： \ne码头官网建设思路：\n一、网站建设需求\n实现全新的公司对外宣传形象；展示公司的创新发展历程，为客户提供技术服务支出等，最直观的让客户了解到e码头是做什么的、e码头做了什么以及能为客户带来什么。\n网站语言版本：中文版\n网站技术类型：静态、动态\n\n二、网站定位\n创新、锐意进取；\n以品牌形象宣传和业务创新为导向；\n结构清晰，层次分明\n\n三、网站颜色\n主色调：蓝色为主；黄色为辅助色，结合e码头logo；\n蓝色更能体现商务性、专业性，简洁朴实；加以黄色点缀，突出重点。\n\n以上各部门收集整理的文案内容，分类打包，一并发至邮箱pll@qhdswl.com\n"]
["网站建设进度表："]
["序号","要求完成时间","任务",null,"责任部门","责任人","实际完成时间","实际完成情况","备注"]
[1,"2019-07-16","官网架构图",null,"行政","彭李麟","2019-07-16","已完成并移交技术部开发"]
[2,"2019-07-23","【e码头】栏目：公司简介、企业文化、荣誉资质内容文字及图片的整理",null,"行政","彭李麟"]
[3,"2019-07-26","【发展历程】：公司创立至今，所有重大事项及内容的罗列",null,"行政","彭李麟"]
[4,"2019-07-31","【业务模块】","新零售、物流、货源文案及图片","市场","戴慕安"]
[5,"2019-07-31",null,"金融相关文案内容","财务","肖湘辉"]
[6,"2019-07-31",null,"技术输出相关文案内容","技术","陈仕科"]
[7,"2019-07-31","【支持与服务】栏目：售前、接入、售后内容的收集与整理",null,"客服","张云"]
[8,"2019-08-16","【新闻动态】栏目：行业政策板块，先将2019年初至今与我司业务相关的行业咨询及相关政策收集并整理，按从新到旧的时间打包，再逐步将2018年的内容补充起来",null,"关务","廖静文"]
[9,"2019-08-16","【联系我们】公司地址板块，在百度地图注册申请我司地址标记点，后续由技术部将地图公司地址植入官网；加入e码头板块的招聘信息整理，后续一并加入官网",null,"行政","何李娜"]
[10,"2019-09-13","负责网站全部开发，包括前端显示和后端管理",null,"技术","黄亚琴\n陈仕科"]
[11,"2019-09-16","网站上线并测试，根据存在的问题进行调整、修改",null,"技术","黄亚琴\n陈仕科"]
[12,"2019-08-23","【首页】分页海报的设计；内页滚动海报的设计",null,"行政","彭李麟"]
[13,"2019-09-13","所有文案内容及图片的上图",null,"行政","彭李麟"]