{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["技术中心项目汇总"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"技术中心项目汇总","index":0,"n_rows":21,"n_cols":8,"rows_kept":21,"flags":["formulas_cached_only"]}
["编号","项目名称","任务列表","描述","开始时间","结束时间","任务状态","任务负责人"]
[1,"wms扫描枪系统","RF枪扫描到错误条码应直接提示","商品下架时候，RF枪扫描到错误条码应直接提示（目前是在输入拣货数量提交后才会跳出提示）","-","2020-10-21","完成","肖文浩"]
[2,"wms作业系统","复核装箱自动扣减","包装复核时，扫描到产品条码时应自动扣减订单明细的数量，比如一个订单只有一款产品，且产品数量是1，在订单复核时，扫描到该产品时，应直接提示复核已完成。（目前系统是扫描产品后，输入数量，手动按回车才能进行下一个产品的复核）","-","2020-10-21","完成","肖文浩"]
[3,"wms作业系统","冻结库存状态异常","冻结部分库存需要把状态改成冻结，而不是正常。","-","2020-10-21","完成","肖文浩"]
[4,"wms作业系统","移动库存增加原因","操作移动库位时需添加移动原因（最好移动原因是可以自行配置的） ","-","2020-10-21","完成","肖文浩"]
[5,"wms作业系统","盘点导出","在操作系统盘点时，盘点表需要添加导出功能，导出表格盘点表。","-","2020-10-21","完成","肖文浩"]
[6,"wms作业系统","盘点完成不扣减库存","盘点完成后点击确认差异与生效后，差异会直接改变目前库存，该操作不合理，应取消。","-","2020-10-21","完成","肖文浩"]
[7,"wms作业系统","出库单导出字段异常","导出出库订单中包材类型与商品条码导出项为空。","-","2020-10-21","完成","肖文浩"]
[8,"wms作业系统","复核装箱明细增加字段","复核装箱明细增加字段","-","2020-10-21","完成","肖文浩"]
[9,"wms作业系统","称重自动完成出区","称重自动完成出区","-","2020-10-21","取消","肖文浩"]
[10,"wms作业系统","订单称重应统一到一个界面","订单称重应统一到一个界面（目前分为称重打单和波次称重，其中波次称重需先录入波次号再录入订单号/跟踪号）","-","2020-10-21","取消","肖文浩"]
[11,"wms作业系统","收货上架确认库存确认完结取消","系统收货上架后操作完成确认库存后还需要确认完结，该步骤与确认库存的意义相同，应取消。","-","2020-10-21","取消","肖文浩"]
[12,"wms作业系统","退货签收后库存不会增加","退货签收后库存不会增加","-","2020-10-21","完成","肖文浩"]
[13,"wms作业系统和扫描枪","增加运单下架功能","增加运单下架功能，同时保留拣货单下架","2020-10-22","2020-10-26","完成","肖文浩"]
[14,"wms作业系统和扫描枪","扫描下架的时候取消扫描库位号的操作","扫描下架的时候取消扫描库位号的操作","2020-10-22","2020-10-26","完成","肖文浩"]
[15,"wms作业系统","普通订单复核装箱箱号在称重前再录入","箱号在明细完成复核后录入","2020-10-22","2020-12-23","完成","肖文浩"]
[16,"wms作业系统","增加展示出区版本的复核装箱页面","增加页面，箱号复核后录入，增加复核完成后导出功能","2020-10-22","2020-12-25","完成","肖文浩"]
[17,"wms作业系统","虚拟一键收货上架","入库单列表页面增加按钮，通过导入excel实现收货上架自动完成","-","-","暂时不做"]
[18,"wms作业系统","虚拟一键下架","出库单列表页面添加按钮，下架不用一个一个扫，直接让这个订单下架","-","-","暂时不做"]
[19,"wms作业系统","称重自动发运","称重自动发运","2020-10-21","2020-10-22","完成","刘诗鹏"]
[20,"wms扫描枪系统","波次下架提示分配分拣框","波次下架，扫描产品输入拣货数量以后应直接提示分配到哪个分拣框内","2020-10-22","2020-10-26","完成","刘诗鹏"]